## Work Packages
Work packages and tasks | Activity code | Responsible person | Involved persons (to be cc'd) | Start |  | End date |  | Monitoring timelines |  |  | Assigned budget | Automatic alert | Current status | Comments
|  |  |  | Planned | Actual | Planned | Actual | Planned activity duration | Actual activity duration | Time gained or lost
WP1 Assessment of available COVID-19 cohorts datasets
T1.1. Inventory of available COVID-19 testing datasets | T1.1
a) Where: Contact RBC to know all testing dataset locations -Is there a centralised dataset hub? | T1.1.1 | Mohammed Semakula (RBC) | Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-11 | 2 | 5 | -3 |  | Running -Check status | In progress
b)How to access them/it? : How to access the datasets, In case they are centralised, Please add the Excel diagram showing its structure (with contact person) | T1.1.2 | Mohammed Semakula (RBC) | Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-01-05 |  | 2021-01-07 |  | 2 | 0 | 2 |  | Running -Check status
c)Activity report : Organize an ad hoc meeting to see if every thing is ready for Lars team | T1.1.3 | Lars Halvorsen (EdenceHealth) | Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-01-12 |  | 2021-01-12 |  | 0 | 0 | 0 |  | Running -Check status
T1.2. Inventory of participating hospitals (Contact names: DG, IT, DM) | T1.2 | [6 empty] | 0 | 0 | 0
1) Where: Contact RBC to initiate contacts with all participating hospitals -to recived their confirmation of participation | T1.2.1 | JB Byiringiro (RBC) | Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, Mohammed, PMO | 2021-01-05 |  | 2021-02-20 |  | 46 | 0 | 46 |  | Running -Check status
2)How to access the data? : Used EMRs, Status, Problems, etc >>> Excel diagram summarizing this info (with contact persons) | T1.2.2 | JB Byiringiro (RBC) | Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, Mohammed, PMO | 2021-01-05 |  | 2021-02-20 |  | 46 | 0 | 46 |  | Running -Check status
3)Activity report : Organize an ad hoc meeting to see if every thing is ready for Lars team taking over (what is still needed to put in place, so Lars can work on the data?) | T1.2.3 | JB Byiringiro (RBC) | Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, Mohammed, PMO | 2021-01-12 |  | 2021-02-20 |  | 39 | 0 | 39 |  | Running -Check status
4) On site hospital visits: Discuss with DG, IT and Data managers >>> Needs/status report per hospital | T1.2.4 | JB Byiringiro (RBC) PMO to organize (Sub-activity details in the budget table) | Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, Mohammed, PMO | 2021-01-18 |  | 2021-02-20 |  | 33 | 0 | 33 |  | Running -Check status
5) 1st hospital workshop : Organize a workshop with hospital DG, IT, DM to inventory what is needed to map data | T1.2.5 | JB Byiringiro (RBC) PMO to organize (Sub-activity details in the budget table) | Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, Mohammed, PMO | 2021-02-01 |  | 2021-02-20 |  | 19 | 0 | 19 |  | Running -Check status |  | Start request to Prime Minister Offices 2 weeks before
6) 2nd hospital workshop : Organize a workshop with hospital IT, DM to set up the process of mapping | T1.2.6 | JB Byiringiro (RBC) PMO to organize (Sub-activity details in the budget table) | Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, Mohammed, PMO | 2021-02-08 |  | 2021-02-20 |  | 12 | 0 | 12 |  | Urgent - This week! |  | Start request to Prime Minister Offices 2 weeks before
7) 3rd hospital workshop : Organize a workshop with hospital IT, DM to test the first mappings done | T1.2.7 | JB Byiringiro (RBC) PMO to organize (Sub-activity details in the budget table) | Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, Mohammed, PMO | 2021-02-15 |  | 2021-02-20 |  | 5 | 0 | 5 |  | Coming in 2 weeks |  | Start request to Prime Minister Offices 2 weeks before
8) Research meeting : Overall research meeting regarding the data gathering | T1.2.8 | JB Byiringiro (RBC) PMO to organize (Sub-activity details in the budget table) | Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, Mohammed, PMO | 2021-02-19 |  | 2021-02-20 |  | 1 | 0 | 1 |  | Coming after 2 weeks |  | Start request to Prime Minister Offices 2 weeks before
T1.3. Assessment of readiness and quality of identified COVID-19 datasets | T1.3 | [6 empty] | 0 | 0 | 0
a) Technical assessment (see technical desk work support budget) | T1.3.1 | Mohammed Semakula (RBC) | Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-01-05 |  | 2021-02-20 |  | 46 | 0 | 46 |  | Running -Check status
b) Assessment report to be discussed in the meeting listed in task T1.1.3 | T1.3.2 | Lars Halvorsen (EdenceHealth) | Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-01-12 |  | 2021-02-20 |  | 39 | 0 | 39 |  | Running -Check status
T1.4. Database structure of listed COVID-19 datasets
a) Running in parallel of the task T1.1.2 | T1.4.1 | Mohammed Semakula (RBC) Lars Halvorsen (EdenceHealth) | Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-01-05 |  | 2021-02-20 |  | 46 | 0 | 46 |  | Running -Check status
WP2 - Hospital Data harmonization framework
T2.1 Technical specification (leverage the White Rabbit and Rabbit-in-A-hat tools from OHDSI) | T2.1 | Lars Halvorsen (EdenceHealth) | JB Byiringiro, CEBE Team, Pascal | 2021-02-01 |  | 2021-02-24 |  | 23 | 0 | 23 |  | Running -Check status
T2.2 Defining the data elements of importance | T2.2 | Lars Halvorsen (EdenceHealth) | JB Byiringiro, CEBE Team, Pascal | 2021-02-01 |  | 2021-02-24 |  | 23 | 0 | 23 |  | Running -Check status
T2.3 OMOP (OHDSI) common data model matching and eventual extension | T2.3 | Lars Halvorsen (EdenceHealth) | JB Byiringiro, CEBE Team, Pascal | 2021-02-01 |  | 2021-02-24 |  | 23 | 0 | 23 |  | Running -Check status
T2.4 ETL and mapping process | T2.4 | Lars Halvorsen (EdenceHealth) | JB Byiringiro, CEBE Team, Pascal | 2021-02-01 |  | 2021-08-27 |  | 207 | 0 | 207 |  | Running -Check status
T2.4.1 ETL and mapping process for POC delivery March (set up with 1 data Source integration f.i. Quest. Or Survey data) |  | Lars Halvorsen (EdenceHealth) | JB Byiringiro, CEBE Team, Pascal | 2021-02-15 |  | 2021-03-26 |  | 39 | 0 | 39 |  | Coming in 2 weeks
T2.4.2 ETL and mapping process for other data source deliveries |  | Lars Halvorsen (EdenceHealth) | JB Byiringiro, CEBE Team, Pascal | 2021-03-03 |  | 2021-08-27 |  | 177 | 0 | 177 |  | Coming after 2 weeks
T2.5 Validation of the conversion (leverage the ACHILLES from OHDSI and other tools) | T2.5 | Lars Halvorsen (EdenceHealth) | JB Byiringiro, CEBE Team, Pascal | 2021-03-01 |  | 2021-03-15 |  | 14 | 0 | 14 |  | Coming after 2 weeks
T2.6 Single dataset test on basic statitistics | T2.6 | Lars Halvorsen (EdenceHealth) | JB Byiringiro, CEBE Team, Pascal | 2021-03-15 |  | 2021-09-27 |  | 196 | 0 | 196 |  | Coming after 2 weeks
T2.6.1 Single dataset test on basic statistics (POC data) |  | Lars Halvorsen (EdenceHealth) |  | 2021-03-26 |  | 2021-04-02 |  | 7 | 0 | 7 |  | Coming after 2 weeks
T2.6.2 Full dataset test on statistics (full integration check on the system) |  | Lars Halvorsen (EdenceHealth) |  | 2021-08-27 |  | 2021-09-27 |  | 31 | 0 | 31 |  | Coming after 2 weeks
WP3 - Central dashboard: Common Interface for data access, querying and analytic including OHDSI tools
T3.1 Architecture design | T3.1 | Lars Halvorsen (EdenceHealth) | JB Byiringiro, CEBE Team, Pascal? Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-01-05 |  | 2021-02-15 |  | 41 | 0 | 41 |  | Running -Check status
T3.2 Data security layer | T3.2 | Lars Halvorsen (EdenceHealth) | JB Byiringiro, CEBE Team, Pascal? Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-01-21 |  | 2021-08-27 |  | 218 | 0 | 218 |  | Running -Check status
T3.2.1 Infra set up (full set up of the solution) |  | Lars Halvorsen (EdenceHealth) |  | 2021-01-21 |  | 2021-08-27 |  | 218 | 0 | 218 |  | Running -Check status
T3.3 Integrating OHDSI interface for data access, query and analysis | T3.3 | Lars Halvorsen (EdenceHealth) | JB Byiringiro, CEBE Team, Pascal? Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-02-15 |  | 2021-03-26 |  | 39 | 0 | 39 |  | Coming in 2 weeks
T3.3.1 Design of Arachne Implementation |  | Lars Halvorsen (EdenceHealth) |  | 2021-02-15 |  | 2021-03-26 |  | 39 | 0 | 39 |  | Coming in 2 weeks
T3.3.2 Arachne Implementation |  | Lars Halvorsen (EdenceHealth) |  | 2021-03-26 |  | 2021-08-27 |  | 154 | 0 | 154 |  | Coming after 2 weeks
T3.4 Other tools integration | T3.4 | Lars Halvorsen (EdenceHealth) | JB Byiringiro, CEBE Team, Pascal? Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-02-15 |  | 2021-04-30 |  | 74 | 0 | 74 |  | Coming in 2 weeks
WP4 -New Data collection, Ethics, data privacy and data related legal issues
T4.1 Ethics | [7 empty] | 0 | 0 | 0
a) Submission to RNEC | T4.1.1 | Clement Bizimana / Clarisse | JB Byiringiro, Mohammed, CEBE Team, Pascal? Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-01-05 |  | 2021-02-15 |  | 41 | 0 | 41 |  | Running -Check status
T4.2 Data privacy | [7 empty] | 0 | 0 | 0
a) Discussions about how to access data - Data privacy and access chart set up | T4.2.1 | Celestin Twizere | JB Byiringiro, Mohammed, CEBE Team, Pascal? Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-01-05 |  | 2021-02-28 |  | 54 | 0 | 54 |  | Running -Check status
T4.3 Data regulations and best practices (Legal framework) | T4.3 | JB Byiringiro | All | 2021-01-05 |  | 2021-02-28 |  | 54 | 0 | 54 |  | Running -Check status
T4.4 Research instruments (Questionnaires): Design, validation, and deployment | T4.4 | [6 empty] | 0 | 0 | 0
a) Individual Technical support work:Preparing the word format questionnaire - Meeting with Edence to anticipate the mapping + programming (C++, Java) for the App (tentative name "CovidApp Rwanda") + Publishing it to Google and Apple Play | T4.4.1 | Celestin Twizere | JB Byiringiro, Mohammed, CEBE Team, Pascal? Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-01-05 |  | 2021-02-05 |  | 31 | 0 | 31 |  | Running -Check status
b) 1st hackaton to review the high level design | T4.4.2 | Celestin Twizere | JB Byiringiro, Mohammed, CEBE Team, Pascal? Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-01-15 |  | 2021-01-15 |  | 0 | 0 | 0 |  | Running -Check status
c) 2nd hackaton to validating the design | T4.4.3 | Celestin Twizere | JB Byiringiro, Mohammed, CEBE Team, Pascal? Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-02-03 |  | 2021-02-03 |  | 0 | 0 | 0 |  | Urgent - This week!
d) Overall research meeting including traning of data supervisors who will train the data collectors | T4.4.4 | Celestin Twizere | JB Byiringiro, Mohammed, CEBE Team, Pascal? Clement, Francine/Clarisse/J Nepo, Lars, Marc, Stefan, Clarisse, PMO | 2021-02-27 |  | 2021-02-27 |  | 0 | 0 | 0 |  | Coming after 2 weeks
T4.5 Data collection | T4.5. | [6 empty] | 0 | 0 | 0
1) Setting up the Call center and other logistics | T4.5.1 | Clement Bizimana / Clarisse | J Nepo | 2021-01-05 |  | 2021-02-20 |  | 46 | 0 | 46 |  | Running -Check status
2) Contact NISR to have access on NISR Database and to identify the needed data ( eg: Tel, locations, etc) | T4.5.2 | Ignace Kabano | J Nepo | 2021-02-03 |  | 2021-02-20 |  | 17 | 0 | 17 |  | Urgent - This week!
3) Perform a sampling on the databases (214 subjects per districts randomly, gender balanced, age group proportional) | T4.5.3 | TBD (ask Francine) | Francine/Clarisse/J Nepo, Stefan, Mediatrice, ACE-DS Team, RBC team, RASD Team | 2021-02-03 |  | 2021-02-20 |  | 17 | 0 | 17 |  | Urgent - This week!
4) Recruitment of 30 Data colleactors (mainly coming from students at CMHS via MeDSAR association or Journalism/UR, but mixed with others) | T4.5.4 | PMO | All | 2021-02-03 |  | 2021-02-15 |  | 12 | 0 | 12 |  | Urgent - This week!
5) Data collectors training (by data supervisors trained for the purposes) | T4.5.5 | Jean Nepo Utumatwishima | Francine/Clarisse/J Nepo, Stefan, Mediatrice, ACE-DS Team, RBC team, RASD Team | 2021-02-16 |  | 2021-02-20 |  | 4 | 0 | 4 |  | Coming in 2 weeks
6) Testing and evaluating the data collectors (using a sample of selected subjects -3 per data collector) | T4.5.6 | Jean Nepo Utumatwishima | Francine/Clarisse/J Nepo, Stefan, Mediatrice, ACE-DS Team, RBC team, RASD Team | 2021-02-25 |  | 2021-02-27 |  | 2 | 0 | 2 |  | Coming after 2 weeks
7)Starting the calls to selected subjects allover the country: purpose of this 1st call being to introduce and explain the study, and to obtain the consent to participate | T4.5.7 | Jean Nepo Utumatwishima | Francine/Clarisse/J Nepo, Stefan, Mediatrice, ACE-DS Team, RBC team, RASD Team | 2021-02-27 |  | 2021-02-28 |  | 1 | 0 | 1 |  | Coming after 2 weeks
8) Buil up the Excel with accepted participants and their network operator, so they can push the App and also the fee | T4.5.8 | Each Data Collector | Supervisors | 2021-02-28 |  | 2021-02-28 |  | 0 | 0 | 0 |  | Coming after 2 weeks
9) Pushing the fee and the Mob Questionnaire to final accepted subjects (Think about WhatsApp notifications) | T4.5.9 | PMO (Viviane/Odile) | Francine/Clarisse/J Nepo, Stefan, Clarisse, MPIs | 2021-02-28 |  | 2021-02-28 |  | 0 | 0 | 0 |  | Coming after 2 weeks
10) Start calling the subjects to check if there are filling in correctly, and no issues (Weekly) | T4.5.10 | Each Data Collector | Francine/Clarisse/J Nepo, Stefan, Clarisse, MPIs | 2021-03-01 |  | 2021-08-31 |  | 183 | 0 | 183 |  | Coming after 2 weeks
T4.6 Data collection monitoring | [7 empty] | 0 | 0 | 0
1) Weekly call (each data collectors call its subject at weekly basis) | T4.6.1 | Each Data Collector | Supervisors, MPIs | 2021-03-01 |  | 2021-08-31 |  | 183 | 0 | 183 |  | Coming after 2 weeks
2) Plan the first face-toface interview (each data collector visit 5 subjects per districts in M1 and M6) | T4.6.2 | Each Data Collector | Supervisors, MPIs | 2021-03-15 |  | 2021-08-31 |  | 169 | 0 | 169 |  | Coming after 2 weeks
3) Face to face interview (Visit or via CHWs for remote area) | T4.6.3 | Each Data Collector | Supervisors, MPIs | 2021-03-15 |  | 2021-08-31 |  | 169 | 0 | 169 |  | Coming after 2 weeks
WP5 - Framework of data analytics
T5.1 Quantitative methods and statistical design | T5.1 | [6 empty] | 0 | 0 | 0
a) Development of the core integrating model (technical support by a dedicated team from investigators) (inspired from our Ghent university work: https://biomath.ugent.be/covid-19-outbreak-modelling-and-control) | T5.1.1 | Mohammed Semakula | MPIs, ACE-DS Team, CEBE Team | 2021-01-05 |  | 2021-02-28 |  | 54 | 0 | 54 |  | Running -Check status
b) 1st hackaton to review the core model (sub-activities and details in the budget table) | T5.1.2 | Mohammed Semakula | MPIs, ACE-DS Team, CEBE Team | 2021-01-28 |  | 2021-01-28 |  | 0 | 0 | 0 |  | Running -Check status
c) 2nd hackaton to validating the core model (sub-activities and details in the budget table) | T5.1.3 | Mohammed Semakula | MPIs, ACE-DS Team, CEBE Team | 2021-02-15 |  | 2021-02-15 |  | 0 | 0 | 0 |  | Coming in 2 weeks
c) Proof-of-concept testing | T5.1.4 | Mohammed Semakula | MPIs, ACE-DS Team, CEBE Team | 2021-02-24 |  | 2021-02-24 |  | 0 | 0 | 0 |  | Coming after 2 weeks
T5.2 Data mining | T5.2 | Mohammed Semakula |  | 2021-03-05 |  | 2021-06-15 |  | 102 | 0 | 102 |  | Coming after 2 weeks
T5.3 Machine learning | T5.3 | [6 empty] | 0 | 0 | 0
a) Development of the core predicting algorithm (GRU BAYES or another) | T5.3.1 | Edward De Brouwer (KU Leuven, Belgium) | MPIs, ACE-DS Team, CEBE Team, RBC | 2021-02-01 |  | 2021-03-15 |  | 42 | 0 | 42 |  | Running -Check status
b) 1st hackaton to review the algorithm in action : test and validate the first iteration | T5.3.2 | Edward De Brouwer (KU Leuven, Belgium) | MPIs, ACE-DS Team, CEBE Team, RBC | 2021-03-25 |  | 2021-03-25 |  | 0 | 0 | 0 |  | Coming after 2 weeks
T5.4 Integrated methodes (and Tools) | T5.4 |  |  | 2021-01-05 |  | 2021-01-15 |  | 10 | 0 | 10
a) Development of thematic analysis -Listing all potential publications topics | T5.4.1 | Each theme leader | All | 2021-01-05 |  | 2021-03-15 |  | 69 | 0 | 69 |  | Running -Check status
b) Thematic breakdown of analysis (5 teams: Gender, Social economic , Mental health, clinical & epidemiology outcomes, Predictions) | T5.4.2 | Each theme leader | All | 2021-03-01 |  | 2021-06-30 |  | 121 | 0 | 121 |  | Coming after 2 weeks
WP6 - Dissemination, Exploitation and Communication
T6.1 Project website with intranet communication tool | [7 empty] | 0 | 0 | 0
a) Contact the website master for design -The web integrated into RBC dashboard ideally | T6.1.1 | Aurore / Mugeni Regina | Contact Mohammed (RBC) to arrange | 2021-01-05 |  | 2021-01-07 |  | 2 | 0 | 2 |  | Running -Check status
b) Website development with documents/archives repository part | T6.1.2 | Aurore / Mugeni Regina | Contact Mohammed (RBC) to arrange | 2021-01-10 |  | 2021-01-30 |  | 20 | 0 | 20 |  | Running -Check status
c) Development of visualisations and integrate it to the Website | T6.1.3 | Aurore / Mugeni Regina | Contact Mohammed (RBC) to arrange | 2021-01-30 |  | 2021-03-25 |  | 54 | 0 | 54 |  | Running -Check status
c) Launching the first version of the website | T6.1.4 | Aurore / Mugeni Regina | Contact Mohammed (RBC) to arrange | 2021-03-30 |  | 2021-03-30 |  | 0 | 0 | 0 |  | Coming after 2 weeks
T6.2 Project Communication and Dissemination Strategy | [7 empty] | 0 | 0 | 0
a) Listing all potential events (conferences, seminars) where the project outcomes can be disseminated | T6.2.1 | Aurore / Mugeni Regina | All | 2021-01-15 |  | 2021-03-30 |  | 74 | 0 | 74 |  | Running -Check status
T6.3 Dissemination and exploitation plan | [7 empty] | 0 | 0 | 0
a) Community linking and dissemination plan: "Bikora Bite" program partnership | T6.3.1 | Aurore / Mugeni Regina | All | 2021-01-05 |  | 2021-01-15 |  | 10 | 0 | 10 |  | Running -Check status
b) Website updating and link with IDRC COVID-19 South programwebsite | T6.3.2 | Aurore / Mugeni Regina | All | 2021-01-05 |  | 2021-01-15 |  | 10 | 0 | 10 |  | Running -Check status
T6.4 Publication plan including self-archiving |  |  |  | 2021-02-01 |  | 2022-09-30 |  | 606 | 0 | 606 |  | Running -Check status
T6.5 Consortium events plan (conferences, workshops, hackathons) |  | PMO (Viviane) | All
a) Listing all planned consortium reaserch meetings (beyond the weekly meetings) | T6.5.1 |  |  | 2021-01-05 |  | 2021-01-15 | [5 empty] | Running -Check status
WP7: Coordination
T7.1 Project oversight and coordination | T7.1 | Francine/Clarisse/J Nepo Birungi (delegate: Stefan) | PMO | 2020-10-01 | 2020-12-15 | 2022-09-30 | 2022-09-30 | 729 | 654 | 75 |  | Running -Check status
T7.2 Project management - Setting up PMO - See details in budget table | T7.2 | Francine/Clarisse/J Nepo Birungi (delegate: Stefan) | PMO | 2020-10-01 | 2020-12-15 | 2022-09-30 | 2022-09-30 | 729 | 654 | 75 |  | Running -Check status
T7.3 Reporting and administartion | T7.3 | Francine/Clarisse/J Nepo Birungi (delegate: Stefan) | PMO | 2020-10-01 | 2020-12-15 | 2022-09-30 | 2022-09-30 | 729 | 654 | 75 |  | Running -Check status
T7.4 Risk managment | T7.4 | PMO | Francine/Clarisse/J Nepo Birungi (delegate: Stefan) | 2020-10-01 | 2020-12-15 | 2022-09-30 | 2022-09-30 | 729 | 654 | 75 |  | Running -Check status
T7.5 Project governance, Consortium managment and internal communication | T7.5 | Stefan Jansen | PMO | 2020-10-01 | 2020-12-15 | 2022-09-30 | 2022-09-30 | 729 | 654 | 75 |  | Running -Check status
T7.6 Alliance managment with ongoing initiatives | T7.6 | Marc / RBC (Mohammed & JB) | PMO | 2020-10-01 | 2020-12-15 | 2022-09-30 | 2022-09-30 | 729 | 654 | 75 |  | Running -Check status
T7.7 Consortium events organization (conferences, workshops, hackathons) | T7.7 | Francine/Clarisse/J Nepo Birungi (delegate: Stefan) | PMO | 2020-10-01 | 2020-12-15 | 2022-09-30 | 2022-09-30 | 729 | 654 | 75 |  | Running -Check status
T7.8 Scalability and sustainability of created framework | T7.8 | Marc / RBC (Mohammed & JB) | PMO | 2020-10-01 | 2020-12-15 | 2022-09-30 | 2022-09-30 | 729 | 654 | 75 |  | Running -Check status
[8 empty] | 0 | 0 | 0
OFFICIAL SIGNATURES
Name of principal researcher: |  | Job Title: |  | Signature
Dr Francine Birungi, MD, MPH, PhD |  | Project Lead PI Head of Department of Epidemiology and statistics Lecturer at University of Rwanda, School of Public Health
Date (Into force as from *): | 2020-10-01 | [6 empty] | Template Revision: 8.6
*Note: This plan is subject to montly revisions
Formulas:
Automatic alert = IF([Start]<TODAY()-1,"Running -Check status",IF([Start]<TODAY()+7,"Urgent - This week!",IF([Start]<TODAY()+14,"Coming in 2 weeks", "Coming after 2 weeks")))

## Deliverables
Work packages and tasks |  | Months
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 Assessment of available COVID-19 cohorts datasets
D1.1. Inventory of available COVID-19 cohorts datasets | 3M | Months 3: D1.1
D1.2. Anticipated list of starting COVID-19 cohorts under EU funding | 6M | Months 6: D1.2, M1.2
D1.3. Assessment Report of readiness and quality of identified COVID-19 cohorts datasets | 9M | Months 9: D1.3
WP2 - Data harmonization framework
D2.1 Technical specification (leverage the open source tools from OHDSI) | 12M | Months 12: D2.1
D2.2 Cohort data elements of relevance for harmonization | 9M
D2.3 Data managment plan | 6M
D2.4 Cohort data harmonization architecture | 24M | Months 13: M2.3
WP3 - Common Interface for data access, querying and analytic including OHDSI tools
D3.2 Technical specification on data security layer | 16M | Months 23: M3.2
D3.3 Technical specification on the integrating OHDSI interface for data access, query and analysis | 24M | Months 15: M3.3
WP4 - Ethics, data privacy and data related legal issues
D4.3 Data regulations and best practices (Legal framework) report | 36M | Months 36: D4.3
WP5 - Framework of validations analytics
D5.1 Quantitative methods and statistical design | 24M | Months 24: M5.1
D5.2 Publication paper on therapeutic outcomes | 36M | Months 24: M5.3a; Months 36: M5.2b
D5.3 Publication paper on immunity assessment (community, healthworkers) | 36M | Months 24: M5.4a; Months 36: M5.2b
D5.4 Publication paper on reproductive health outcomes | 36M | Months 24: M5.5a; Months 36: M5.5b
WP6 - Dissemination, Exploitation and Communication
D6.1 Project website with intranet communication tool | 3M | Months 6: M6.1
D6.2 Project Communication and dissemination and exploitation strategy | 6M | Months 12: D6.2
D6.3 Publication plan including self-archiving | 18M | Months 12: D6.4
D6.4Consortium events plan (conferences, workshops, hackathons) reports | 36M | Months 36: D6.5
WP7: Coordination
D7.1 Consortium Agreement | 3M
D7.2 Charter for cohorts joining the INTERCOHORT database | 6M
D7.3 Global work plan (including all meetings plan) | 6M | Months 6: D7.3a, M7.3; Months 36: D7.3b
D7.4 Project governance, Consortium managment and internal communication plan | 6M | Months 6: D7.5a, M7.5; Months 36: D7.5b